## Process Flow
Step | Who | Action | Ticket Status | Activities/Tasks to complete before moving to next step | Notes / Artifacts* (* indicates artifact is required by auditors)
1 | Requester | Create request ticket | New | Complete request
2 | Support Team | Assign ticket to designated IT team | New | Follow normal process to assign to designated team.
3 | Designated IT Team | Designate team member to be ticket owner | New | Follow normal process to assign to designated team member.
4 | Ticket Owner | Review request | In Process | 1. Review contents of request 2. Follow up with requester for additional information as needed. 3. Engage other IT team members as needed to determine size and scope of change. Work with DEV manager to assign resource as needed. 4. Assess scope of change - Project or Non-Project (see tab Project VS Non-Project)
4a | Ticket Owner | If PROJECT, follow SDLC Process flow. | Completed | Follow the SDLC Process flow to create SDLC request. | 1. Request ticket must be stored with the SDLC request as the original request* 2. Other documentation, screen shots, etc. should be added to project in attachments.
4b | Ticket Owner | If NON-PROJECT, notify requester with next steps | In Process | 1. Notification to end user should also include manager (CC). 2. Next steps should - who will be doing the work to resolve issues, summary of what changes will be made, how this will be verfied as correct (tested) and approx. ETA for completion.
5 | DEV Resource | Complete changes | In Process | 1. Complete changes in development test environment (where applicable). 2. Complete unit testing in development test environment (where applicable). 3. Document what was changed (module, screen, job name, etc). 4. Notify Ticket Owner when completed. | What was changed must be documented in ticket*
6 | Ticket Owner | Validate changes | In Process | 1. Validate changes. 2. Notify requester that changes are complete. 3. Schedule deployement with implementer. | Validation of changes must be documented in ticket*
7 | Implementer | Deploy changes | In Process | Deploy changes
8 | Ticket Owner | Confirm implementation was successful | Completed | 1. Confirm with requester that changes were successfully implemented. 2. Document validation. | Implementation validation must be documented in ticket*

## Project VS Non-Project
Project VS Non-Project | Criteria | Examples
Project | Request involves changes to a financial system such as: AR, AR, GL, Tax, Costing | Change to customer invoice; change to ACH payments file; update to GL consolidation
Project | Request resolution will require > 10 hours to complete | Combination of programming and testing > 10 hours
Project | Request impacts an entire department or multiple departments | Change to sales order maintenance in QAD (impacts customer service, credit, accounting)
Non-Project | Request is for an AUTOSYS (Batch system) job change. | Update the email address recipient on a job; change the run time on a job, create a new cyberquery batch job.
Non-Project | Request is for a minor change to shop floor, QAD, website with no financial impact. | Add a field to a non-financial report, change the size of a field on a screen.