## Process Flow
Step | Who | Where | Action | Gate | Project Status | Project Task | Activities/Tasks to complete before moving to next step | Notifications | Notes
1 | BSA / BSA MGR | Request | Create request | BSA / Assigned BSA | n/a | n/a | 1. Select NEW, Initiation Request. 2. See tab "Creating a Request". 3. Once request is completed, click Save & Submit. |  | If request is completed by BSA Manager, then step 1a is needed. If request is completed by BSA, then request immediately moves to Gate "Assigned BSA"
1a | BSA MGR | Request | Assign BSA to Request (step is needed if Request was created by BSA MGR) | Assigned BSA | n/a | n/a | 1. Update "Assigned BSA". 2. Click Save & Approve. | You have to option to notify the requester and/or other future approvers. | No notification to Assigned BSA unless you click "Notify other approvers" (this also notifies BSA MGR and DEV MGR).
2a | BSA | Request | Convert Request to Project | Assigned BSA | REQUIREMENTS PLANNING | Analysis/Requirements | 1. Gather necessary information about the request; perform impact analysis (size and scope of the request). 2. When BSA has sufficient information AND IS READY TO START WORKING ON SPECS, turn request into project. 3. See tab "Creating Project from Request". | BSA manager and DEV manager are notified via project alerts.
2b | BSA | Project | Complete requirements | Assigned BSA | REQUIREMENTS PLANNING | Analysis/Requirements | 1. Complete required artifacts - Functional specifications, Test plan, BRD, etc. depending on size and scope of request. 2. Update Complete Date on task Analysis/Requirements.
2c | BSA | Request | Move request to BA MGR approval | BSA MGR - Review / QA | RESOURCE PREP (automatically set when Complete Date is updated on Analysis/Requirements task) | Resource Prep | 1. Click Save & Approve. 2. Add note if needed. Click "Notify other pending approvers". Click Approve. | BSA Manager is notified they have a request to approve
3 | BSA MGR | Request | BSA MGR approves | BSA MGR - Review / QA | RESOURCE PREP | Resource Prep | 1. Ensure project has all of the necessary information. 2. Review artifacts; schedule peer review as needed 3. Save & Approve. 4. Add note if needed. Click "Notify other pending approvers". Click Approve. | DEV Manager is notified they have a request to update.
4 | DEV MGR | Project | Assign resources | Dev Mgr - Review Estimate | Resource Prep | Resource Prep | Assign resource(s) to tasks Resource Prep and Design/Code/Unit Test | Added resources are notified via project alerts
5a | DEV resource(s) | Project | DEV resource prepares estimate | Dev Mgr - Review Estimate | Resource Prep | Resource Prep | 1. Schedule meeting with BSA to review requirements. BSA and Resource(s) work together to ensure requirements are complete. 2. Prepare estimate. Add start and end date and hours to task. 3. Update Complete Date on Resource Prep task. | DEV mgr and BSA are notified that status has changed via project alerts. | 1. After DEV estimate has been added, BSA updates start and end dates for BA/QA Testing task and for Business End-User Testing task. 2. BSA communicates target date to end -user.
5b | DEV MGR | Request | DEV mgr approves estimate | Dev Mgr - Review Estimate | DESIGN/CODE/UNIT TEST (automatically set when Complete Date is updated on Resource Prep task) | Design / Code / Unit Test | In request, click Save & Approve. | Resource(s) are notified via project alerts.
6 | DEV resource | Project | DEV resource completes coding | BSA Approves Test | DESIGN/CODE/UNIT TEST | Design / Code / Unit Test | 1. Complete development and unit test. 2. Update Complete Date on DEV/Code /Unit test task. | BSA is notified via project alerts.
7a | BSA | Project, Request | BSA completes QA testing | BSA Approves Test | BA / QA Test (automatically set when Complete Date is updated on Design / Code / Unit Testing task) | BA / QA Testing | 1. Complete BSA testing. 2. Update Completion Date on BA / QA Testing task. 3. In Request - BSA approves.
7b | BSA | Request, Project | BEU approves | BEU Approval | BEU Test (automatically set when Complete Date is updated on BA / QAD Testing task) | Business End-User Testing | 1. In Project - BSA marks completion date on BEU task and adds implementer to Implementation task 2. In Request - BSA approves | Implementer is notified via project alerts.
8 | Implementor | Project | Implementor deploys | BEU Approval | Implementation (automatically set when Complete Date is updated on Business End-User Testing task) | Implementation | 1. Implementor updates Complete Date on Implementation task. 2. Implementor changes status to Implemented. | All team members are notified via project alerts.
9 | BSA | Request | Approved | Approved |  |  | 1. BSA requests confirmation from BEU that changes are in production and working correctly. 2. BSA approves request.
10 | BSA | Project | Project is closed |  | Completed |  | 30 days past implementation, BSA changes status to Completed

## Creating a Request
Step | What
1 | Click "New", select "Initiation Request"
2 | Complete information. Required fields are highlighted in yellow. If request is created by BSA, also fill in Assigned BSA. When all required fields are entered, click Save & Submit.
Click Submit
3 | Request can now be updated with notes and attachments as needed.
3a | To add an attachment, go to Attachments tab, click ADD. All 3 fields must be filled in. Click SAVE.
This is the Attachments tab after attachment was added.
3b | To add a Note, go to the Notes tab. Select "Add Note". Subject and message must be filled in. Click SAVE.
This is the Notes tab after note was added.

## Creating Project from Request
Step | What
1 | In the request, go to Associations tab, then select NEW
2 | You are now ready to create a project.
2a | Schedule From: defaults to today's date. Date is used as the starting point for tasks.
2b | Project Templates: select from the drop down list.
2c | Project Category - will automatically populate based on template selected.
2d | Select elements to copy into project:
TASKS
PROJECT CALENDAR
ALERTS
click NEXT
3 | Copy data from Request to Project.
Click the checkbox next to SOURCE FIELD to select all.
Click Copy Request Attachments and Copy Request Notes. These options will be available if you added attachments and/or notes to the request.
Click Next
4 | Complete the project.
Project Number: SSS + YYYYMMDD + NN where
SSS = the system (MXO = MX Open, QAD = QAD, OPN = non-ERP, BI = BI
NN = a sequential number, starting with "01" to make the project number unique
Title: this defaults to the Title from the request. Add PROJECT NUMBER to the beginning of the title
All other fields will default from the Request.
This is the Associations tab in the Request, after the project was completed.

## Tasks Roles & Responsibilities
Task | Who is responsible for completing task | Activities | Artifacts (*audit requirement) (see tab Artifacts for more information)
Analysis / Requirements | BSA | 1. BSA completes all artifacts necessary for development resources to estimate. 2. BSA adds spec/test plan/artifacts to project attachments. 3. BSA updates COMPLETE DATE on task Analysis/Requirements. | This can include the following (depending on the size and scope of the project): - Original request from end user * - Functional spec* - Test plan* - Wire frames - mock ups of screens, reports, web pages, other displays - Use cases - specific end user scenarios that exercise the entire process, not just what it being changed - DRD - Data requirements document - BRD - Business requirements document
Resource Prep | DEV MGR, DEV Resource(s), BSA | 1. DEV MGR adds DEV Resource(s) to Design / Code / Unit Test task. 2. DEV Resource(s) meet with BSA to review project requirements. BSA add details/updates to spec and test plan as needed. 3. BSA adds updated spec/test plan/artifacts to project attachments. 4. DEV Resource(s) updates task Design/Code/Unit Test: SCHEDULE HOURS, START DATE, TARGET DATE. 5. DEV Resource(s) updates COMPLETE DATE on task Resource Prep. | Updated spec and test plan May also include technical documentation depending on size and scope of request.
Design / Code / Unit Test | DEV Resource(s) | 1. DEV Resource(s) completes development and unit testing. 2. DEV Resource(s) adds completed DEV test plan to project attachments. 3. DEV Resource(s) adds change control document to project attachments. 4. DEV Resource(s) updates COMPLETE DATE on task Design/Code/Unit Test | Completed DEV test plan. Change Control document.*
BA / QA Testing | BSA | 1. BSA completes QA testing. 2. BSA adds completed BSA test plan to project attachments. 3. BSA updates COMPLETE DATE on task BA/QA testing. 4. BSA notifies end user that QA testing is complete and schedules times to review end user's testing requirements. | Completed BSA test plan* Documentation/work instructions (as needed) for the Analysis sharepoint site
Business End-User Testing | BSA | 1. BEU completed review and sends approval. 2. BSA adds BEU approval to project attachments. 3. BSA add implementer(s) to task Implementation. 4. BSA notifies or meets with implementer(s) to decide when deployment is appropriate. 5. BSA updates COMPLETE DATE on task Business End-user Testing. | BEU approval*
Implementation | Implementer(s), BSA | 1. Implementer(s) deploy changes. 2. Implementer(s) adds implementation confirmation to project attachments. 3. BSA validates production with end-user and receives confirmation. 4. BSA adds production validation confirmation to project attachments. | Production validation confirmation*
Project Meetings / Assigned Tasks | ALL | Placeholder for misc. meetings, other activities not associated with any of the above tasks.

## Artifacts
Artifact (* required by auditors) | Completed by | Purpose | Content
Project Initiation (pre-project approval) - inception, business idea approval, solution, high level functional (BRD), scope, financial definition (including acquisition of equipment, licensing, contractor/consultant services), AR | BSA, BEU | Project Initiation flow - Inception, Idea approval by business, solution search, functional definition, scope definition, financial definition, AR. Applies for large projects or for Medium where there is significant cost. | See tab Project Initiation
Request Initiation* | BEU / BSA | High level requirements. To be expanded upon by BSA for the BRD where applicable and Functional. | From end-user: Specific function/screen/site, current state, what changes are requested, expected result
Business requirements (BRD) | BSA | Where applicable, describes the changes requested and how it will be delivered. Can include User Stories, use cases, business rules, process flow, error handling. BEU signs off on BRD before Functional is completed. | BRD - higher level, for the end user to agree to. What are the inputs, what are the outputs, what is the flow of data? Separate, formal agreement is based on the size of the projects. For smaller requests, is part of the functional.
Functional requirements | BSA | Requirements at a function, screen, field level. Opportunity for standardization of what should be included for each type of change, like a checklist (new field on a screen, customization of a screen, new table, new ERP screen, new website, etc). | Project identifier, Security, Batch processes, database requirements, specific applications/functions/site, source table/fields and how to find data, screen layouts, reporting requirements, Error handling, Assumptions, Multi-language, user help, version control, application/functions impacted by change, config/gen code,
Wire frames/prototypes | BSA | As needed, templates, screen layout, output layouts. | Screen layout, process flow, sample screens - depending on the size and scope of project, could be incorporated into the BRD.
Technical requirements | DEV / Infrastructure / SCG | as needed, Includes documentation, data flow diagrams, could be an existing artifact to be updated or a new one, system architecture | Environment, platform, DB, dev tool, ancilliary systems, hardware requirements, Data model, Data flow, integration points, web services.
Test plan | BSA | Another opportunity for a checklist, list of what tests are needed depending on what it being requested. | Testing sequence, test prep, test flow, assumptions, test environment requirements, test cases/scenarios (including all impacted functions/systems).
Communication plan | BSA | Who will be notified, at what point in the process and what is the content of the notification. Templates. | Key stakeholders, timeline of communication, method of communication (email, sharepoint, teams, etc), content of communication. Needed for major changes that impact large groups of end users.
Completed test plan - DEV | DEV | Test plan (original) completed | Same info as test plan with test results.
Completed test plan - BSA | BSA | Test plan (original) completed | Same info as test plan with test results.
Test plan validation - end user | BSA | End user test validation (their own test cases) | End user's test scenarios, as needed
User approval* | BEU | Must show what is being changed and who approved it. | What was changed, who approved it.
Implementation plan* | DEV / Infrastructure / SCG | List of all components to be deployed. Different implementation plan contents depending on what is being deployed and where. Could include tasks for BSA, end user, batch jobs, Database set up, etc. | a plan for each system being changed; each plan includes components being changed, based on the system selected. QAD, MXOpen, Shop floor, database, web, BI. Will need more information about what components for each system.
Implementation confirmation* | Implementers, BSA, End user | Could be a date/time box on the implementation plan to show when it is deployed and another to show when the changes are confirmed in production (by BSA or end user). | Email from end user with direction from BSA, screen print of new screens, CQ, DB, jobs
Work instructions/Documentation/work flows | BSA, End User | As needed, could be new or updates to existing. | Work instructions - BSA provides details of changes to end user who is then responsible for updating their own work instructions. For new systems, BSA provides list of components and how to use each. End user incorporates into their own intenal documentation. Can include administration guides.
Help desk instructions | BSA | Needed when change could result in end user issues/questions, or to give support a heads up. Include where to find work instructions/process flows. Part of communication plan? | What is changed, who to contact, impact level (who to call and how critical), where to find documentation and system requirements.